## Slide 1
PROJECT PRISM
Global Revenue Intelligence Engine
Phase 1: Win/Loss Analysis
Leadership Team
Pete Mansel (CRO)
Mike Duda (VP RevOps)
Brad Towers (SE Lead UK/ANZ)
Steve Logan (CIO)
CONFIDENTIAL

## Slide 2
Data Rich, Insight Poor
Thousands of data points across global regions, but our Win/Loss intelligence is manually dependent. Deal review notes and competitor intelligence are locked in text fields — impossible for our teams to manually read and synthesize everything.
We need automated intelligence to surface patterns, detect at-risk deals, and guide strategic revenue decisions in real-time.
100-500
Opps Per Week
3
Global Regions
0
Automated Insights
?
Deals At Risk

## Slide 3
AI-Driven Revenue Intelligence
1
Ingest
Pull raw text from Win/Loss notes and Deal Review forms automatically
2
Analyze
Use LLMs to read context, sentiment, and nuance across every opportunity
3
Synthesize
Aggregate into structured themes, cluster win/loss reasons by region
4
Report
Deliver weekly Global Intel Report — dashboard + auto-gen deck for ELT

## Slide 4
Win/Loss Intelligence MVP
Win/Loss Theme Analysis
Region breakdown of why we win/lose
At-Risk Deal Detection
AI scans for risk markers in notes
Competitor Intelligence
Auto extraction of competitor mentions
Market Signal Detection
Early detection of emerging objections
Data Sources
SFDC Win/Loss
Notes, Deal
Review Forms
Outputs
Interactive
Dashboard, Auto-
gen PPTX, Email
Regions
NA, UK, ANZ
Cadence
Weekly
automated run

## Slide 5
System Architecture — Phase 1
DATA SOURCES
Win/Loss Notes | Deal Review Forms | Clari Copilot (Phase 2)
RevOps
INGESTION
CSV Export | Parse & Normalize | PII Flagging | Validation
Mike / RevOps
LLM ENGINE
Theme Extraction | Risk Detection | Competitor Intel | Market Signals
Provider-Agnostic
Brad / SE
OUTPUT
Interactive Dashboard | Auto-Gen PPTX | Email Distribution
All

## Slide 6
Provider-Agnostic by Design
Swap providers via configuration — no code changes required
Claude
Phase 1 Default
✓
GPT
Alternative
✓
Gemini
Alternative
✓
A common LLMProvider interface abstracts all API calls. Change provider by updating a single environment variable.

## Slide 7
End-to-End Processing Flow
01
Export
Pull data from SFDC
→
02
Parse
Normalize & clean
→
03
Validate
Check quality & schema
→
04
Analyze
LLM processing
→
05
Report
Generate outputs
Batch Processing: 20-30 Opportunities per Run
Our system processes Win/Loss data in manageable batches to ensure consistent quality, avoid rate limits, and maintain audit trails. Each batch is tracked from ingestion through reporting.

## Slide 8
Weekly Global Intel Report
Top Win Themes
AI-powered analytics
Speed to deploy
Enterprise integration
ROI clarity
Top Loss Themes
Implementation complexity
Cost vs. alternative
Timing mismatch
Security concern
Report includes detailed regional breakdowns, competitive positioning, and actionable insights for leadership reviews.

## Slide 9
Workstreams & Ownership
Workstream | Responsible | Accountable | Key Deliverable
Data Schema & Export | Mike / RevOps | Pete | SFDC definitions, CSV automation
Data Pipeline | Brad / SE | Pete | Parser, normalizer, PII flagger
LLM Analysis Engine | Brad / SE | Pete | Provider layer, prompts
Report Generation | Brad / SE | Pete | Dashboard, auto-gen PPTX, email
Security & Hosting | Steve / IT | Steve | Privacy review, hosting, API keys

## Slide 10
Phase 1 — 4-Week Sprint
Week 1
Define schema
CSV export setup
Security review
Begin pipeline build
Week 2
LLM provider layer
Prompt engineering
Batch processing
Hosting decision
Week 3
Dashboard build
PPTX report build
Historical data test
Validate with RevOps
Week 4
ELT presentation
Feedback & iterate
Deploy automation
Retrospective
Target: First Global Intel Report delivered Week 4

## Slide 11
Phase 1 KPIs
90%
Risk Accuracy
100%
ELT Adoption
<24h
Time to Insight
2x
Gap Detection Speed

## Slide 12
The 3-Horizon Strategy
H1
Intelligence Engine
Now
AI-powered win/loss analysis, automated risk detection, competitive intel extraction
MVP
Phase 1
Weekly Reports
H2
Intervention Layer
Q2 '26
Real-time alerts, deal coaching, predictive interventions, embedded in Salesforce
Real-time
Alerts
Integration
H3
Agentic Growth Force
H2 '26
Autonomous deal management, predictive pipeline, automated opportunity creation
Autonomous
Growth
Future-proof

## Slide 13
Data Privacy Considerations
Action Required
Review LLM API data privacy policies
Validate data residency requirements
Obtain legal & compliance sign-off
Document data handling agreements
Built-in Safeguards
PII scrubbing in pipeline
No customer data in prompts
Secure environment variables
Architecture Mitigations
Provider-agnostic for on-prem option
Data minimization by default
Comprehensive audit logging

## Slide 14
Let's Make It Happen
Mike
VP RevOps
Define field list
Create CSV export
Share sample data
Brad
SE Lead UK/ANZ
Build pipeline
Build LLM engine
Deliver prototype
Steve
CIO
Data privacy review
Hosting decision
API key mgmt
Pete
CRO
Sponsor & blockers
Define ELT needs
Present to ELT
Target: First Global Intel Report delivered Week 4