PROJECT PRISM

Phase 1 Implementation Plan

Win/Loss Intelligence Engine

CONFIDENTIAL — INTERNAL USE ONLY

February 2026

Project Team

Pete Mansel, CRO  |  Mike Duda, VP RevOps

Brad Towers, SE Leader UK/ANZ  |  Steve Logan, CIO

Document Version 1.0

# 1. Executive Summary

Project Prism is an AI-powered intelligence initiative designed to transform unstructured Salesforce field data into actionable strategic insights for Executive Leadership and GTM teams. This document provides the detailed implementation plan for Phase 1: the Win/Loss Intelligence Engine.

The Opportunity: With the recent rollout of structured Deal Review Forms and the systematic capture of Win/Loss notes directly in Salesforce, we are now collecting thousands of data points about every opportunity globally. However, this data remains locked in text fields — impossible for any human team to read, synthesize, and act on at scale. Project Prism closes this gap.

What Phase 1 Delivers

- Weekly Global Intel Report: An automated, AI-generated analysis of win/loss themes by region (NA, UK, ANZ), delivered as both a PowerPoint deck for ELT meetings and an interactive HTML dashboard for on-demand exploration.

- At-Risk Deal Radar: AI-powered sentiment scanning of active opportunities to surface hidden risks not reflected in standard forecast stages.

- Market Signal Detection: Early identification of emerging competitor tactics, product gap themes, and customer objection patterns across the global pipeline.

Phase 1 Data Scope Phase 1 focuses exclusively on Salesforce data: Win/Loss Notes and Deal Review Forms. Clari Co-Pilot call transcript integration is planned for Horizon 2 (Q2 2026).

# 2. Phase 1 Scope & Objectives

## 2.1 In Scope

- Data Sources: SFDC Opportunity Win/Loss Notes (free-text), SFDC Deal Review Form fields (structured + free-text), standard Opportunity metadata (stage, amount, region, owner, dates).

- Analysis: Win/loss theme categorization, regional segmentation, sentiment-based risk scoring, competitive intelligence extraction, product gap identification.

- Outputs: Weekly PowerPoint executive report, interactive HTML dashboard, structured JSON data archive for historical trending.

- Regions: North America (NA), United Kingdom (UK), Australia/New Zealand (ANZ).

## 2.2 Out of Scope (Phase 1)

- Clari Co-Pilot call transcript ingestion (Horizon 2)

- Salesforce Agentforce integration for automated actions (Horizon 2)

- Automated coaching nudges or enablement triggers (Horizon 2)

- Agentic sales agents for outbound / NCA (Horizon 3)

- Real-time / daily reporting cadence (weekly only for Phase 1)

## 2.3 Success Criteria

- Accuracy: 90%+ accuracy in win/loss theme categorization when validated against a manual sample review by RevOps.

- Adoption: ELT and GTM Leaders actively reference the weekly report in forecast calls within 4 weeks of launch.

- Risk Detection: At-risk radar identifies deals that subsequently slip or are lost in 75%+ of cases.

- Timeliness: Full pipeline analysis and report generation completes within 2 hours of data export, every week.

# 3. Data Requirements Specification

This section defines the exact data fields required from Salesforce. This is the primary deliverable Steve (CIO) and Mike (VP RevOps) need to action.

## 3.1 Required SFDC Opportunity Fields

The following standard Opportunity object fields are required for every opportunity in the analysis window:

| Field Name | SFDC API Name (Expected) | Type | Purpose |
| --- | --- | --- | --- |
| Opportunity ID | Id | ID | Unique identifier for deduplication |
| Opportunity Name | Name | Text | Display and reference in reports |
| Account Name | Account.Name | Text | Group by customer for pattern analysis |
| Account Industry | Account.Industry | Picklist | Industry-level trend identification |
| Region | Region__c or Territory | Text | Required: NA, UK, or ANZ segmentation |
| Opportunity Owner | Owner.Name | Text | Rep-level performance analysis |
| Stage | StageName | Picklist | Current pipeline position |
| Close Date | CloseDate | Date | Time-based trending and forecasting |
| Amount | Amount | Currency | Revenue weighting for impact analysis |
| Win/Loss Status | IsWon / IsClosed | Boolean | Closed Won vs. Closed Lost classification |
| Probability | Probability | Percent | Cross-reference with AI risk scoring |
| Created Date | CreatedDate | DateTime | Deal cycle length calculation |
| Product Line | Product__c (TBC) | Picklist | Product-level win/loss patterns |
| Competitor | Competitor__c (TBC) | Text | Competitive intelligence mapping |

## 3.2 Win/Loss Notes Fields

These are the unstructured text fields where reps document why deals were won or lost. These are the primary input for AI analysis.

| Field Name | SFDC API Name (Expected) | Type | Notes |
| --- | --- | --- | --- |
| Win/Loss Reason (Picklist) | Win_Loss_Reason__c (TBC) | Picklist | Structured reason codes if they exist (e.g., Price, Product, Competitor) |
| Win/Loss Notes | Win_Loss_Notes__c (TBC) | Long Text | Primary free-text field — the core input for AI analysis |
| Loss Competitor | Loss_Competitor__c (TBC) | Text | Specific competitor named in loss scenarios |

## 3.3 Deal Review Form Fields

Action Required — Mike Duda / Steve Logan The Deal Review Form schema is needed to complete this specification. Please provide the full list of field names, field types, and dropdown option values from the new OPP Deal Review form in Salesforce. This is a critical path item for Phase 1.

Based on the CRO vision document, the Deal Review Form likely captures structured assessments across several deal health dimensions. The following is an anticipated schema to be validated:

| Expected Category | Anticipated Fields | AI Use Case |
| --- | --- | --- |
| Executive Engagement | Level of exec sponsor alignment, Access to power | Risk scoring — lack of executive alignment is a top risk factor |
| Competitive Landscape | Known competitors, Competitive positioning rating | Competitive intelligence aggregation by region |
| Technical Fit | Product fit assessment, Integration complexity | Product gap identification and technical risk detection |
| Commercial / Pricing | Pricing competitiveness, Discount level | Pricing pressure trend analysis |
| Decision Criteria | Evaluation criteria clarity, Decision timeline | Deal velocity prediction and stall detection |
| Champion Strength | Champion identified, Champion influence rating | Risk scoring — weak champion = elevated risk |
| Next Steps / Blockers | Defined next steps, Identified blockers | Stalled deal detection from absent next steps |
| Overall Deal Health Score | Composite score or RAG rating | Cross-reference with AI-generated risk assessment |

## 3.4 Data Export Requirements

Export Format

- CSV is the recommended format for Phase 1 (simplest to parse, universally compatible).

- UTF-8 encoding required to preserve special characters in notes.

- One row per Opportunity (all fields flattened, including Win/Loss Notes and Deal Review fields).

- Separate files acceptable if needed (Opportunities + Win/Loss + Deal Reviews), linked by Opportunity ID.

Export Scope

- Closed Deals: All Closed Won and Closed Lost opportunities from the last 12 months (for historical baseline analysis and model validation).

- Open Pipeline: All active opportunities (any stage) for the At-Risk Radar analysis.

- Ongoing Weekly: Delta export of opportunities modified in the last 7 days (or full refresh if simpler to implement).

Export Mechanism (Recommendation)

- Phase 1a — Manual Report Export (Fastest to Start): RevOps creates a saved SFDC report with all required fields. Export is triggered manually each week as a CSV download. This gets us running immediately with zero IT build effort.

- Phase 1b — Scheduled Automated Export: IT (Steve) configures a scheduled SFDC report or Data Loader export that automatically delivers the CSV to a shared location (e.g., secure S3 bucket or shared drive) on a weekly cadence.

- Future — Direct API Integration: For Horizon 2+, move to Salesforce REST API integration using simple-salesforce (Python) for real-time data access.

# 4. Technical Architecture

## 4.1 Recommended Approach: Two-Stage Build

We recommend a phased technical approach that prioritises speed-to-value while building toward full automation:

Stage A — Rapid Prototype (Week 1–2)

- Tool: Claude Project (claude.ai) with custom System Prompt and Knowledge Base.

- Method: Upload the SFDC CSV export into a Claude Project. The system prompt instructs Claude to analyse every opportunity and return structured JSON output with win/loss themes, risk scores, and regional breakdowns.

- Purpose: Validate that the AI analysis produces accurate, actionable insights before investing in automation. This is the “proof of concept” that demonstrates value to ELT within days, not weeks.

- Output: Raw structured analysis that Brad manually formats into the first draft PowerPoint and HTML dashboard.

Stage B — Automated Pipeline (Week 2–3)

- Tool: Python script using Anthropic Claude API (claude-sonnet-4-5-20250929).

- Method: A Python pipeline that reads the SFDC CSV, sends batched opportunity data to the Claude API with structured prompts, receives JSON analysis, aggregates results, and automatically generates the PowerPoint deck and HTML dashboard.

- Purpose: Full automation — one command generates the entire weekly report end-to-end.

- Output: Weekly PowerPoint (.pptx) + interactive HTML dashboard, ready for distribution.

## 4.2 System Architecture

The Phase 1 pipeline follows a straightforward four-stage data flow:

| Stage | Component | Technology | Description |
| --- | --- | --- | --- |
| 1. Ingest | Data Import | Python (pandas) | Read SFDC CSV export, validate schema, clean data, segment by region |
| 2. Analyse | AI Analysis Engine | Claude API (Sonnet 4.5) | Multi-pass analysis: individual opp scoring, then regional theme synthesis |
| 3. Aggregate | Data Aggregation | Python (pandas, JSON) | Merge individual analyses, compute regional summaries, trend calculations |
| 4. Generate | Report Generation | Python (python-pptx, HTML/Jinja) | Produce PowerPoint deck + interactive HTML dashboard from aggregated data |

## 4.3 Technology Stack

| Component | Technology | Rationale |
| --- | --- | --- |
| Programming Language | Python 3.11+ | Industry standard for data processing; rich ecosystem for SFDC, AI, and reporting |
| AI Model | Claude Sonnet 4.5 (via Anthropic API) | Best balance of speed, cost, and analytical depth for structured data analysis at scale |
| Data Processing | pandas | De facto standard for tabular data manipulation in Python |
| PowerPoint Generation | python-pptx | Mature library for programmatic PPTX creation with full formatting control |
| HTML Dashboard | Jinja2 templates + Chart.js | Generates self-contained HTML files with interactive charts, no server required |
| Orchestration | Cron (Linux) or Task Scheduler (Windows) | Simple scheduled execution for weekly cadence |
| Version Control | Git (private repo) | Track changes to prompts, analysis logic, and report templates |

## 4.4 Claude API Prompt Engineering Strategy

The quality of Prism’s analysis depends entirely on the design of the prompts sent to Claude. We will use a multi-pass approach:

Pass 1 — Individual Opportunity Analysis

Each opportunity is sent to Claude with its full context (metadata + notes + deal review fields). Claude returns a structured JSON object containing:

- Win/Loss Theme Classification: Primary and secondary themes from a predefined taxonomy (see Section 5).

- Sentiment Score: A 1–10 score reflecting the overall health/sentiment of the deal notes.

- Risk Factors: Array of identified risk indicators (e.g., “no executive sponsor mentioned”, “competitor undercutting on price”).

- Competitor Intelligence: Named competitors and their tactics/positioning as described in notes.

- Product Gap Signals: Specific product capabilities or features cited as missing or inadequate.

- Key Quote: The most illustrative sentence or phrase from the notes (for use in reporting).

Pass 2 — Regional Synthesis

After all individual opportunities are analysed, the aggregated results for each region are sent to Claude for high-level synthesis. Claude produces:

- Top 5 win themes and top 5 loss themes for the region, with supporting evidence.

- Emerging trends — themes that are increasing in frequency vs. prior periods.

- Regional competitive landscape summary.

- Product gap priority list, ranked by frequency and deal value impact.

Pass 3 — Executive Summary Generation

The full global dataset is sent to Claude for a final executive summary pass, producing a 3–5 paragraph narrative suitable for the opening slide of the PowerPoint deck and the CRO’s weekly briefing.

# 5. Win/Loss Analysis Framework

## 5.1 Theme Taxonomy

Every won or lost deal will be classified into one or more of the following standardised theme categories. This taxonomy ensures consistency across regions and over time, enabling trend analysis.

| Theme Category | Description | Example Signal in Notes |
| --- | --- | --- |
| Pricing / Commercial | Deal outcome driven by pricing, discounting, or commercial terms | "Lost on price", "competitor came in 30% lower", "budget constraints" |
| Product Capability | Decision driven by product features, functionality, or roadmap | "Missing X feature", "product couldn’t do Y", "best-in-class functionality" |
| Product Gap | Specific missing capability that directly caused a loss or risk | "No native integration with Z", "lacking mobile support", "API limitations" |
| Competitive Displacement | Competitor won or is winning based on their offering or tactics | "Went with [Competitor]", "incumbent advantage", "competitor FUD" |
| Relationship / Trust | Outcome influenced by existing relationships, trust, or brand perception | "Strong existing relationship", "trusted advisor status", "new vendor risk" |
| Technical Fit / Integration | Decision driven by technical architecture, integration, or implementation | "Complex integration requirements", "didn’t fit tech stack" |
| Timing / Budget | Deal stalled or lost due to timing, budget cycles, or priority shifts | "Budget frozen", "project delayed to next FY", "not a priority right now" |
| Sales Execution | Outcome influenced by the quality of the sales process itself | "Great demo sealed it", "lost momentum", "couldn’t get to power" |
| Implementation / Services | Concerns about implementation complexity, services, or support | "Worried about go-live timeline", "services cost too high" |
| Champion / Stakeholder | Outcome driven by presence or absence of an internal champion | "Our champion left", "strong internal advocate", "no clear buyer" |

## 5.2 Risk Scoring Methodology

For active (open) opportunities, Prism will generate a composite Risk Score on a 1–10 scale (10 = highest risk). The score is derived from the following weighted risk indicators:

| Risk Indicator | Weight | Detection Method |
| --- | --- | --- |
| Negative sentiment in recent notes | 25% | AI sentiment analysis of last 3 note entries |
| No executive sponsor identified | 20% | Absence of exec-level stakeholder mentions in notes or deal review |
| Stalled next steps / no recent activity | 15% | No note updates in 14+ days; or notes indicate “waiting” / “no response” |
| Active competitor named and gaining traction | 15% | Competitor mentioned with positive positioning in customer notes |
| Product gap cited as concern | 10% | Feature or capability gap identified in notes or deal review |
| Misaligned close date vs. activity level | 10% | Close date within 30 days but deal review shows early-stage indicators |
| Weak or absent champion | 5% | No internal champion identified or champion described as “lukewarm” |

Validation Approach Risk scores will be validated in Phase 1 by comparing AI-generated risk assessments against actual deal outcomes over the trailing 90 days. Deals flagged as high-risk (7+) that subsequently closed lost or slipped will be measured against the 75% accuracy target.

## 5.3 Competitive Intelligence Extraction

Prism will maintain a rolling competitive intelligence matrix, automatically populated from deal notes. For each named competitor, the system will track:

- Win rate against that competitor (by region and globally).

- Primary tactics and positioning used by the competitor (extracted from notes).

- Most common loss themes when losing to that competitor.

- Emerging competitor FUD or new messaging patterns detected across multiple deals.

## 5.4 Product Gap Tracking

Every product gap or missing capability mentioned in win/loss notes will be captured, categorised, and ranked by:

- Frequency: How many deals cite this gap.

- Revenue Impact: Total pipeline value of deals affected by this gap.

- Regional Distribution: Whether the gap is global or region-specific.

This data feeds directly into the Product Feedback Loop identified in the CRO’s strategic vision, giving Product leadership data-backed prioritisation input.

# 6. Output Specifications

## 6.1 Weekly PowerPoint Deck

The primary ELT deliverable is a concise, visually clear PowerPoint deck designed to be presented in under 10 minutes during forecast calls or ELT meetings.

Slide Structure

| Slide # | Title | Content |
| --- | --- | --- |
| 1 | Cover | Project Prism — Weekly Global Intel Report, date range, regions covered |
| 2 | Executive Summary | 3–5 paragraph AI-generated narrative of the week’s key findings |
| 3 | Global Win/Loss Overview | High-level win/loss counts and rates by region; bar or donut chart |
| 4 | Win Themes — NA | Top 5 win themes for North America with frequency and example quotes |
| 5 | Loss Themes — NA | Top 5 loss themes for North America with frequency and revenue impact |
| 6 | Win Themes — UK | Top 5 win themes for UK |
| 7 | Loss Themes — UK | Top 5 loss themes for UK |
| 8 | Win Themes — ANZ | Top 5 win themes for ANZ |
| 9 | Loss Themes — ANZ | Top 5 loss themes for ANZ |
| 10 | At-Risk Radar | Top 10 highest-risk open deals with risk score, amount, and primary risk factor |
| 11 | Competitive Landscape | Competitor win/loss matrix; emerging competitor tactics |
| 12 | Product Gap Tracker | Top product gaps ranked by frequency and revenue impact |
| 13 | Trend Analysis | Week-over-week changes in key themes; emerging or declining patterns |
| 14 | Recommended Actions | AI-suggested actions for sales leadership based on findings |

## 6.2 Interactive HTML Dashboard

The HTML dashboard is a self-contained file (no server required) that provides on-demand, drill-down exploration of the same data. It is designed for GTM leaders who want to explore beyond the PowerPoint summary.

Dashboard Features

- Region Filter: Toggle between Global, NA, UK, and ANZ views.

- Time Range Selector: Filter by current week, last 4 weeks, last quarter, or custom date range.

- Win/Loss Theme Charts: Interactive bar charts showing theme frequency and revenue impact, clickable to see underlying deals.

- At-Risk Deal Table: Sortable, searchable table of flagged deals with risk scores, amounts, and risk factor breakdowns.

- Competitor Matrix: Visual competitor comparison showing win rates, key tactics, and trend direction.

- Product Gap Heatmap: Grid showing product gaps by frequency and revenue impact, coloured by severity.

- Trend Sparklines: Week-over-week mini charts for key metrics showing directional movement.

Technical Implementation

- Single HTML file with embedded CSS and JavaScript (Chart.js for visualizations).

- Data embedded as a JSON object within the HTML — no external dependencies or API calls.

- Can be emailed, posted to SharePoint/Confluence, or opened locally in any browser.

- Dark theme option available (toggle) for presentation/screen-sharing contexts.

# 7. Team Responsibilities

## 7.1 RACI Matrix

| Task | Brad Towers (SE) | Mike Duda (RevOps) | Steve Logan (IT) | Pete Mansel (CRO) |
| --- | --- | --- | --- | --- |
| Define data export schema | C | A | R | I |
| Build SFDC report / export | I | C | R | I |
| Provide Deal Review Form schema | I | R | C | I |
| Build Claude analysis prompts | R | C | I | I |
| Build Python processing pipeline | R | I | C | I |
| Design PowerPoint template | R | C | I | A |
| Build HTML dashboard | R | I | I | I |
| Validate analysis accuracy | C | R | I | I |
| Weekly report generation | R | C | I | I |
| Present findings to ELT | C | C | I | A |
| Iterate based on ELT feedback | R | C | I | A |

R = Responsible (does the work)  |  A = Accountable (owns the outcome)  |  C = Consulted  |  I = Informed

## 7.2 Role Details

Brad Towers (SE Leader UK/ANZ) — Technical Build Lead: Owns the end-to-end technical implementation. Designs Claude prompts, builds the Python pipeline, creates both the PowerPoint and HTML dashboard generation logic. Primary point of contact for all technical decisions.

Mike Duda (VP RevOps) — Data & Process Owner: Owns the data schema definition and validation. Ensures the SFDC data is clean, complete, and exported correctly. Validates AI analysis accuracy against ground truth. Defines the Deal Review Form field mappings.

Steve Logan (CIO) — Infrastructure & Security: Responsible for SFDC report/export setup, data security compliance, API access provisioning (if needed), and any infrastructure for automated scheduling.

Pete Mansel (CRO) — Executive Sponsor: Sets the strategic direction, defines what ELT needs from the report, and champions adoption. Provides feedback on report content and format.

# 8. Implementation Timeline

Phase 1 is designed for a 3-week sprint to first ELT delivery, with a 1-week buffer for iteration.

## Week 1 — Foundation & Prototype

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon–Tue | Define and validate data export schema with RevOps/IT | Mike + Steve | Agreed field list and export format |
| Mon–Tue | Provide Deal Review Form field definitions and dropdown values | Mike | Form schema document |
| Tue–Wed | Build SFDC report with all required fields; initial export | Steve | First CSV data export |
| Wed–Thu | Set up Claude Project prototype; design analysis system prompt | Brad | Working Claude Project with test analysis |
| Thu–Fri | Run prototype against exported data; validate output quality | Brad + Mike | Sample analysis results for review |

## Week 2 — Pipeline Build & Report Design

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon–Tue | Build Python pipeline: data ingestion, Claude API integration | Brad | Working data processing pipeline |
| Tue–Wed | Design and implement PowerPoint generation logic | Brad | Auto-generated PPTX from analysis data |
| Wed–Thu | Build interactive HTML dashboard | Brad | Self-contained HTML dashboard file |
| Thu | Full end-to-end pipeline test with real data | Brad + Mike | Complete report set (PPTX + HTML) |
| Fri | RevOps accuracy validation — compare AI output to manual review | Mike | Validation report with accuracy metrics |

## Week 3 — Refinement & ELT Delivery

| Day | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| Mon–Tue | Iterate on prompt design based on validation feedback | Brad | Refined analysis prompts |
| Tue–Wed | Polish report formatting and dashboard design | Brad | Production-quality outputs |
| Wed | Internal team review — dry run of ELT presentation | All | Feedback incorporated |
| Thu | Generate first official Weekly Global Intel Report | Brad | V1 report package |
| Fri | Present to ELT for feedback | Pete + Team | ELT feedback captured |

## Week 4 — Buffer & Operationalise

- Incorporate ELT feedback into prompts, report format, and dashboard.

- Set up weekly automation (cron job or scheduled task).

- Document the operational runbook for ongoing weekly execution.

- Establish the weekly cadence: data export Monday AM, report delivery Monday PM or Tuesday AM.

# 9. Immediate Action Items

The following actions are required to unblock Phase 1. These items should be completed within the first 3 business days.

| # | Action Item | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| 1 | Provide full Deal Review Form schema (all field names, types, dropdown options) | Mike Duda | Day 2 | Not Started |
| 2 | Provide list of Win/Loss reason codes (if picklist exists in SFDC) | Mike Duda | Day 2 | Not Started |
| 3 | Build SFDC report containing all fields from Section 3 of this document | Steve Logan | Day 3 | Not Started |
| 4 | Export initial CSV dataset (12 months closed + all open pipeline) | Steve Logan | Day 3 | Not Started |
| 5 | Confirm region field mapping (field name and valid values for NA/UK/ANZ) | Mike Duda | Day 1 | Not Started |
| 6 | Provision Claude API key or confirm usage of existing Anthropic account | Brad Towers | Day 1 | Not Started |
| 7 | Confirm data handling / security requirements for AI processing | Steve Logan | Day 2 | Not Started |
| 8 | Review and approve this implementation plan | Pete Mansel | Day 1 | Not Started |

Critical Path Item Items 1–4 are on the critical path. The prototype cannot begin until the first data export (Item 4) is available, and the analysis prompts cannot be finalised until the Deal Review Form schema (Item 1) is documented.

# 10. Risks & Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Poor data quality — Win/Loss notes are sparse, inconsistent, or missing for many deals | Medium | High | Run data quality audit on initial export. Identify gaps. Work with RevOps to improve note-taking compliance. Use Deal Review Form structured fields as fallback when notes are thin. |
| AI hallucination / inaccurate classification — Claude misinterprets notes or invents themes | Low | High | Multi-pass validation: RevOps manually reviews a sample each week. Use structured output (JSON schema) to constrain Claude’s responses. Include confidence scores. |
| Data security concerns — sending deal data to external AI API | Medium | Medium | Use Anthropic’s enterprise terms (data not used for training). Explore Anthropic’s data processing agreement. Anonymise customer names if required. |
| Delayed data export — IT cannot deliver the SFDC export on time | Medium | Medium | Start with manual CSV export from a saved SFDC report (no IT build required). Automate later. |
| Low ELT adoption — report is produced but not used in decision-making | Low | High | Pete (CRO) to champion adoption. Design report for the 10-minute forecast call format. Iterate based on ELT feedback. |
| API cost overruns — processing thousands of opportunities weekly | Low | Low | Use Claude Sonnet (cost-efficient). Batch processing. Estimated cost: under $50/week for 1,000 opportunities. |
| Deal Review Form schema changes mid-flight | Medium | Medium | Build flexible prompt templates that reference field names dynamically. Changes require only config updates, not code rewrites. |

# 11. Estimated Costs

Phase 1 is designed to be extremely lean. The primary costs are personnel time (already allocated) and Claude API usage.

| Item | Estimate | Frequency | Notes |
| --- | --- | --- | --- |
| Claude API usage (Sonnet 4.5) | $30–$75/week | Weekly | Based on processing 500–2,000 opportunities per run with multi-pass analysis |
| Python infrastructure | $0 | One-time | Runs on existing hardware; no cloud hosting required for Phase 1 |
| Brad’s development time | ~40 hours total | One-time | Weeks 1–3 build effort, then ~2 hours/week for maintenance |
| Mike’s validation time | ~2–3 hours/week | Weekly | Review and validate AI analysis output during initial weeks |
| Steve’s IT setup time | ~4–6 hours total | One-time | SFDC report creation and export configuration |

ROI Context At an estimated $50/week in API costs, Project Prism replaces what would require a full-time analyst (or more) to manually read and synthesise every deal note across three regions. The intelligence produced is not just faster — it is more comprehensive than any human could deliver, covering 100% of the pipeline every single week.

# 12. Looking Ahead — Horizon 2 & 3

Phase 1 is the foundation. Once the Intelligence Engine is proven, the following capabilities are planned:

Horizon 2 — The Intervention Layer (Q2 2026)

- Ingest Clari Co-Pilot call transcripts to validate rep notes against actual customer conversations.

- Integrate with Salesforce Agentforce for automated corrective actions (auto-tasks, coaching nudges).

- Move from weekly to daily reporting cadence.

Horizon 3 — The Agentic Growth Force (H2 2026)

- Deploy autonomous agentic sales agents for New Logo Acquisition and expansion.

- 100% TAM coverage through AI-driven outbound at scale.

- Target: 50% reduction in Revenue Acquisition Cost (RAC).

End of Document — Project Prism Phase 1 Implementation Plan v1.0