## Slide 1
Project Prism
Global Revenue Intelligence Engine
Project Status Update | February 2026
Brad Towers | SE Lead, UK & ANZ | Sponsored by Pete Mansel (CRO)

## Slide 2
The Problem We're Solving
Revenue Blind Spots
Win/loss analysis is manual, inconsistent, and happens too late to change outcomes.
14-Day Cycle Pressure
Our high-velocity model means a single day of inaction is 7% of the entire sales cycle.
Scattered Intelligence
Deal insights live in notes, spreadsheets, and tribal knowledge — not in one actionable view.

## Slide 3
What is Project Prism?
An AI-powered revenue intelligence engine that transforms raw Salesforce data into actionable deal insights, risk alerts, and CRO-ready briefings — automatically.
Salesforce
CSV / BigQuery
→
AI Analysis
(Claude / Gemini)
→
Risk & Theme
Detection
→
CRO
Dashboard
Key Outputs
Deal Health Scores (0-100) for every opportunity
Win/loss theme extraction across all regions
Risk signals: ghost deals, stalls, missing champions
Portfolio-level CRO briefing with P1/P2/P3 actions
Competitor intelligence aggregation

## Slide 4
What's Been Built
React Dashboard
Live dark-theme UI with region tabs, AI briefing panel, risk radar, and trend charts
LLM Analysis Engine
Multi-provider (Claude/Gemini/OpenAI) with batched processing and retry logic
CSV Ingestion Pipeline
Salesforce field mapping, PII scrubbing, data quality scoring
Simpro Stage Model
Full 5-stage sales process (Discovery → Closed Won) with required field validation
MRR Calibration
All thresholds tuned for high-velocity 14-day cycles and MRR focus
Firebase Infrastructure
Cloud Functions, Firestore, Storage — deployed and live at project-prism.web.app

## Slide 5
Calibrated for Simpro's Speed
AI threshold has been tuned for a 14-day target cycle and MRR revenue model.
Metric
Before
After
Why
Ghost Deal Alert
14 days silence
3 days silence
3 days = 20% of full cycle
Enterprise Threshold
>$25K deal value
>$2K MRR
MRR is our revenue metric
Cycle Stall Warning
Not tracked
5+ days in stage
Target ~2-3 days per stage
Competitive Blind Spot
>$10K deals
>$500 MRR deals
Competitors matter at all tiers
Action Urgency (P1)
This week
TODAY
1 day = 7% of the deal

## Slide 6
Aligned to Pete's AI-First CRO Vision
Prism maps directly to the three pillars from Pete's "The AI-First CRO" framework.
Signal
Architecture
AI extracts themes, risk signals, and competitor intel from every deal automatically.
Decision
Governance
Structured P1/P2/P3 recommendations ensure the right action happens at the right time.
Kaizen Revenue
Engine
Continuous analysis loop: every CSV upload feeds back into pattern detection.
6 Features Built
3 Partially Built
11 New Features Mapped

## Slide 7
Data Requirements: What We Need
A detailed spec document has been prepared for the data warehouse team.
Quick Start: 7 Fields to Get Running
Opportunity ID
REQUIRED
Opportunity Name
REQUIRED
Stage
REQUIRED
Expected MRR
REQUIRED
Created Date
REQUIRED
Close Date
REQUIRED
Win/Loss Reason
REQUIRED
Enrichment Fields (20+ more)
Deal review notes & manager notes
Last activity date
Sales rep / opportunity owner
Lead source & deal type
Economic buyer identified
Competitor mentioned
Forecast category
Region / geography
Full specification: Prism-Data-Requirements-Spec.docx

## Slide 8
How We Get the Data In
Option A: Manual CSV Upload
Export from Salesforce/BigQuery, upload via dashboard. Great for pilot testing with a subset of data.
Zero dev effort
Ready now
Option B: Scheduled BigQuery Export
Daily automated extract from BigQuery to Cloud Storage bucket. Prism picks up new files automatically.
Data team: 2-4 hours
1-2 weeks
Option C: Direct API Integration
Real-time Salesforce webhook or BigQuery streaming connector. Full automation, zero manual steps.
Engineering sprint
4-6 weeks
Recommendation: Start with Option A (pilot), move to Option B for production.

## Slide 9
Next Steps & Timeline
This Week
Data team delivers Quick Start CSV extract (7 fields)
Run first live analysis through the pipeline
Review results with Pete and Mike
Weeks 2-3
Add enrichment fields (notes, activity dates, reps)
Set up scheduled BigQuery export (Option B)
Tune AI prompts based on real data feedback
Weeks 4-6
Pete's 20 Questions Dashboard (killer feature)
Multi-region rollout (UK, AU, NZ, NA, IE)
Weekly automated CRO briefings

## Slide 10
What We Need to Move Forward
Data / SFDC Team
Deliver the Quick Start CSV extract (7 fields) from BigQuery this week
Pete (CRO)
15-minute review of first live analysis results to validate AI accuracy
Mike (RevOps)
Confirm region mapping and sales stage naming conventions match Salesforce
Steve (CIO)
Approve scheduled BigQuery export path for Phase 2 automation
Goal: First live revenue intelligence report by end of this week.

## Slide 11
Where We Really Are
60% to Working Prototype
Integration & Tuning
What's Done
Full React dashboard with dark theme UI
Multi-provider LLM engine (Claude/Gemini/OpenAI)
CSV parser with Simpro field mapping
MRR-calibrated risk detection & thresholds
Firebase infrastructure deployed & live
Pete's CRO framework mapped to features
What Remains
End-to-end test with real Simpro data
BigQuery column name mapping validation
2-3 rounds of LLM prompt tuning
Edge cases: missing fields, stage names
Report transformer → dashboard rendering
Demo polish and stakeholder walkthrough
The gap between "code compiles" and "works with real data" is where 60-70% of the effort lives.

## Slide 12
Known Integration Risks
These are the areas most likely to need iteration once real data flows through the system.
HIGH
BigQuery Column Mapping
The CSV parser expects specific Salesforce column names. BigQuery exports will likely use different naming conventions. First fix we'll make.
MEDIUM
LLM Output Quality
AI analysis will be structurally correct but needs 2-3 prompt tuning rounds to produce genuinely useful Simpro-specific insights.
MEDIUM
Edge Cases in Real Data
Deals with missing fields, unexpected stage names, currency formatting, and empty win/loss reasons will need graceful handling.
HIGH
Report Transformer
The layer that converts backend LLM output into the dashboard's expected shape is the most fragile link. Likely needs debugging with real payloads.

## Slide 13
Realistic Path to Live Demo
Target: Week of March 16th — first live revenue intelligence demo for Pete.
Week 1
Break Things
Receive Quick Start CSV from data team
Get Firebase emulators running locally
Push first real CSV through the pipeline
Fix column mapping mismatches
Identify and log every failure point
Week 2
Fix & Tune
Iterate on LLM prompt quality
Handle edge cases from real data
Fix dashboard rendering with live output
Tune risk thresholds against actual deals
Second data extract with enrichment fields
Week 3
Demo Ready
Polish dashboard with real data flowing
Walk Pete through live analysis results
Validate AI accuracy against known outcomes
Document what worked and what didn't
Plan Phase 2 automation path
Key dependency: Data team delivers Quick Start extract this week. Clock starts then.

## Slide 14
"The engine is built.
We need real fuel.
Give me the data and three weeks,
and I'll show you live
revenue intelligence."
Target Demo: Week of March 16, 2026